## Sheet1
Project Planner | [5 empty] | Hours spent per month
Hours spent per month
Task | Hours Estimated for Task | Deadline (date) | Hours Spent (calculated) | (Over)/ Under budget | Cumulative Hours | Jun '20 | Jul '20 | Aug '20 | Sep '20 | Oct '20 | Nov '20 | Dec '20 | Jan '21 | Feb '21 | Mar '21 | April '21 | May '21 | Notes
Create Website | 2 | 2020-06-08 | 5 | -3 | 5 |  | 3 | 5 |  | 4 | 3
Research Cipy Right Laws for Books | 3 | 2020-06-21 |  | 3 | 5 | 1
Create general Table of Contents | 1.5 | 2020-06-21 |  | 1.5 | 5
Decide Which Composers | 1 | 2020-06-25 |  | 1 | 5
research Composers | 10+ | 2020-07-08 | 0 | #VALUE! | 5
Research Legality of Using Music Clips | 3 | 2020-07-08 | 0 | 3 | 5
Reach out to marin Alsop and Julien Bencichou | 3 | 2020-07-08 | 0 | 3 | 5
Decide Upon a technology Method | 6 | 2020-07-15 | 0 | 6 | 5
Choose a Title | 1 | 2020-07-30 | 0 | 1 | 5
Decide on Medium/Software for Book | 2 | 2020-07-30 | 0 | 2 | 5
Determine how to do illustrations/pictures | 3 | 2020-07-30 | 0 | 3 | 5
Formally complete a draft | 25 | end of summer | 0 | 25 | 5
Complete 50% of visual aids | 25 | end of summer | 0 | 25 | 5
|  |  | 0 | 0 | 5
|  |  | 0 | 0 | 5
|  |  | 0 | 0 | 5
|  |  | 0 | 0 | 5
|  |  | 0 | 0 | 5
|  |  | 0 | 0 | 5
|  |  | 0 | 0 | 5
|  |  | 0 | 0 | 5
|  |  | 0 | 0 | 5
|  |  | 0 | 0 | 5
TOTALS | 75.5 |  | 5 | #VALUE!